## Copy of Progress
Overview of feature readiness per module
| Total Features | Done (OK) | Pending | Overall %
| 70 | #REF! | #REF! | #VALUE!
# | Module | Total Features | Done (OK) | % Complete | Status | Notes
1 | Dashboard | 5 | 0 | 0% | In Progress | Quick-launch OK; others pending or removed
2 | Achievement & Leaderboard | 5 | 5 | 100% | Not Started | Pop-up, combine badges — all pending
3 | Progress Tracking | 8 | 8 | 100% | In Progress | Body Metrics sub-features pending
4 | Training Program | 7 | 7 | 100% | In Progress | Add/start restrictions need fixing
5 | Exercise Library | 3 | 0 | #REF! | In Progress | Images/GIFs for some exercises missing
6 | Exercise Session | 11 | 0 | 0% | Complete | All sub-modes complete
7 | Post-Exercise Summary | 3 | 0 | #REF! | Not Started | Wording, photo limit, route — all pending
8 | Fitness AI Chatbot | 5 | 4 | 80% | Not Started | All features pending
9 | User Customization | 9 | 6 | 66.67% | In Progress | Only Settings (notif + logout) done
10 | Social — Feed | 2 | 0 | #REF! | Not Started | Both features pending
11 | Social — Groups | 5 | 0 | 0% | Complete | All complete
12 | Social — Community Leaderboard | 2 | 0 | 0% | Complete | All complete
13 | Social — Messages | 2 | 0 | 0% | Complete | All complete
14 | Social — Profile | 3 | 0 | 0% | Complete | All complete
TOTAL |  | 70 | #REF! | #VALUE!

## Progress Table
Problem Statement | Objectives | Scopes | Features | Target Date of Completion | Date of Completion | Remarks | Comments
How to elevate the way Makaton is integrated and utilized in learning instruction that will effectively support teacher-guided Makaton instruction critical for special needs of learners with communicative impediments? | To elevate the way Makaton is integrated and utilized in learning instruction by designing and developing a web-based multimodal machine learning-based Makaton learning support system that will effectively support teacher-guided Makaton instruction critical for special needs of learners with communicative impediments. | Implementation of Overall MakaLearn System - Account Management Module - Makaton Learning Content Management Module - Interactive Makaton Symbol Playground and Activity Module - Makaton Hand Gesture Recognition and LLM-Based Corrective Feedback Module | OVERALL MAKALEARN SYSTEM | September 23, 2026 |  | Partially finished | Most runtime features are committed, but model sample preparation and evaluation are not evidenced in Git.
|  |  | - Teacher and Administrator Account and Profile Management | August 26, 2026 | 2026-09-15 12:00 | Finished | 341f379 — Admin account/role controls and Settings redesign.
|  |  | - Teacher Account Management and Admin Content Oversight | August 27, 2026 | 2026-09-15 12:00 | Finished | 341f379 — Admin account/role controls and Settings redesign.
|  |  | - Makaton Multimedia Learning Content and Symbol Card Management | August 29, 2026 | 2026-09-16 12:00 | Finished | d21d819 — Media removal controls and lesson activity/practice link.
|  |  | - Makaton Content Category and Lesson Management | August 31, 2026 | 2026-09-17 12:00 | Finished | 554dbd1 — Lesson editor freeze fixed.
|  |  | - Activity Creation, Drafting, Library, and Player | September 3, 2026 | 2026-09-03 12:00 | Finished | aa7d392 — Database-only records and shared-activity permissions.
|  |  | - Interactive Makaton Symbol Learning and Audio Playback | September 7, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - MSAV-Based Symbol Arrangement Validation | September 8, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - Makaton Hand Gesture Recognition Model Development | September 14, 2026 |  | Partially finished | 9fba95c adds the integrated model, but sample collection, dataset preparation, and evaluation commits were not found.
|  |  | - Camera-Based Makaton Gesture Practice, Recognition, and Feedback Display | September 18, 2026 | 2026-09-17 12:00 | Finished | fa11da1 — Guided gesture-recognition session and retry flow.
|  |  | - LLM-Based Corrective Feedback | September 20, 2026 | 2026-09-14 12:00 | Finished | b9f9cd1 — Corrective-feedback API, safeguards, and local fallback.
| To design, develop, and evaluate a web-based interactive multimodal Makaton symbol learning module integrated with the Makaton Symbol Arrangement and Validation Algorithm that will help enable repeated Makaton symbol association, arrangement validation, and reinforcement among SPED learners. | Implementation of Interactive Makaton Symbol Playground and Activity Module - Symbol Exploration Playground - Interactive Symbol Activities - Symbol Audio Playback - MSAV Algorithm Integration | INTERACTIVE MAKATON SYMBOL PLAYGROUND AND ACTIVITY MODULE | September 8, 2026 | 2026-09-03 12:00 | Finished | Latest required child evidence: aa7d392 — Database-only records and shared-activity permissions.
|  |  | Activity Creation and Drafting | September 2, 2026 | 2026-09-03 12:00 | Finished | Latest required child evidence: aa7d392 — Database-only records and shared-activity permissions.
|  |  | - Create manual activities | September 1, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Generate activity drafts from learning items | September 2, 2026 | 2026-08-17 12:00 | Finished | edc3446 — Working AI activity drafting from learning items.
|  |  | - Create shared or private visibility option | September 2, 2026 | 2026-09-03 12:00 | Finished | aa7d392 — Database-only records and shared-activity permissions.
|  |  | - Save activity records | September 2, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | Activity Library and Player | September 3, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - Create and view available activities | September 3, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Create activity player | September 3, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - Create answer activity questions | September 3, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - View final score | September 3, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | Makaton Symbol Exploration Playground | September 4, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - View available Makaton/PECS symbol cards | September 4, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - Filter symbol cards by category | September 4, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - Select symbol cards to communicate | September 4, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - Arrange selected symbol cards | September 4, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - Clear selected symbol cards | September 4, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | MSAV Symbol Arrangement Validation | September 8, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - Validate symbol arrangements using rule-based logic | September 8, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - Display correct or incorrect feedback | September 8, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | Drag-and-Drop Activity | September 5, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - Drag symbol cards to answers | September 5, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - Drop symbol cards into target areas | September 5, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - Check dropped answers | September 5, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - Show correct or incorrect feedback | September 5, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - Display activity score | September 5, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | Matching-Type Activity | September 6, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - Match words to symbol cards | September 6, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - Check matched answers | September 6, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - Show correct or incorrect feedback | September 6, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | - Display activity score | September 6, 2026 | 2026-07-01 12:00 | Finished | d14cf96 — Match/drag-and-drop layouts and scoring.
|  |  | Fill-in-the-Blank Activity | September 7, 2026 | 2026-07-01 12:00 | Finished | ba8cd1b — Fill-in-the-blank questions and result feedback.
|  |  | - Select the missing word or symbol | September 7, 2026 | 2026-07-01 12:00 | Finished | ba8cd1b — Fill-in-the-blank questions and result feedback.
|  |  | - Complete symbol-based sentence prompts | September 7, 2026 | 2026-07-01 12:00 | Finished | ba8cd1b — Fill-in-the-blank questions and result feedback.
|  |  | - Check fill-in-the-blank answers | September 7, 2026 | 2026-07-01 12:00 | Finished | ba8cd1b — Fill-in-the-blank questions and result feedback.
|  |  | - Show correct or incorrect feedback | September 7, 2026 | 2026-07-01 12:00 | Finished | ba8cd1b — Fill-in-the-blank questions and result feedback.
|  |  | - Display activity score | September 7, 2026 | 2026-07-01 12:00 | Finished | ba8cd1b — Fill-in-the-blank questions and result feedback.
|  |  | Makaton Symbol Audio Playback | September 7, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - Play audio for selected Makaton/PECS cards | September 7, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - Play audio in activities | September 7, 2026 | 2026-06-26 12:00 | Finished | bbe0912 — Student mode plus gesture references and audio.
|  |  | - Play assembled sentence audio | September 7, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
| To develop and evaluate an optimized computer vision-based Makaton hand gesture recognition model integrated with generative AI-based corrective feedback that will improve Makaton hand gesture practice. | Implementation of Makaton Gesture Recognition and LLM-Based Corrective Feedback Module - Camera-Based Makaton Hand Gesture Practice - Makaton Hand Gesture Recognition Model Integration - LLM-Based Corrective Feedback | MAKATON GESTURE RECOGNITION AND LLM-BASED CORRECTIVE FEEDBACK MODULE | September 20, 2026 |  | Partially finished | Runtime recognition and corrective feedback are committed; the offline model-development workflow is only partly evidenced.
|  |  | Makaton Hand Gesture Recognition Model Development | September 14, 2026 |  | Partially finished | 9fba95c adds the integrated model, but the full data/training/evaluation sequence is not present in commits.
|  |  | - Record and validate hand gesture samples | September 9, 2026 |  | Not yet evidenced | No committed gesture-sample recording or validation artifact was found through HEAD 554dbd1.
|  |  | - Extract and prepare the hand landmark dataset | September 10, 2026 |  | Not yet evidenced | No committed hand-landmark dataset preparation artifact was found through HEAD 554dbd1.
|  |  | - Develop and train baseline and optimized models | September 12, 2026 |  | Partially finished | 9fba95c adds a trained Keras model and converted weights, but not separate baseline and optimized training evidence.
|  |  | - Evaluate and compare model performance and training behavior | September 13, 2026 |  | Not yet evidenced | No committed model comparison or training-behavior evaluation report was found through HEAD 554dbd1.
|  |  | - Select the best-performing model for system integration | September 14, 2026 | 2026-09-04 12:00 | Finished | 9fba95c — Adds best_makalearn_gesture_model.keras and deployed runtime weights.
|  |  | Camera-Based Gesture Display | September 15, 2026 | 2026-07-01 12:00 | Finished | 9f0bcdd — Camera lifecycle handling and practice UI.
|  |  | - Create open webcam preview | September 15, 2026 | 2026-06-22 12:00 | Finished | 8593052 — MediaPipe hand tracking, camera controls, and landmark display.
|  |  | - Show live camera frame | September 15, 2026 | 2026-06-22 12:00 | Finished | 8593052 — MediaPipe hand tracking, camera controls, and landmark display.
|  |  | - Display hand landmark overlay | September 15, 2026 | 2026-06-22 12:00 | Finished | 8593052 — MediaPipe hand tracking, camera controls, and landmark display.
|  |  | - Stop camera preview | September 15, 2026 | 2026-07-01 12:00 | Finished | 9f0bcdd — Camera lifecycle handling and practice UI.
|  |  | Makaton Gesture Reference Panel | September 16, 2026 | 2026-06-30 12:00 | Finished | 8a98fec — Gesture reference media and learner practice layout.
|  |  | - Select gesture reference item | September 16, 2026 | 2026-06-26 12:00 | Finished | bbe0912 — Student mode plus gesture references and audio.
|  |  | - View reference image or video | September 16, 2026 | 2026-06-30 12:00 | Finished | 8a98fec — Gesture reference media and learner practice layout.
|  |  | - Create gesture instruction | September 16, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - Play gesture audio | September 16, 2026 | 2026-06-26 12:00 | Finished | bbe0912 — Student mode plus gesture references and audio.
|  |  | Hand Visibility Indicator | September 16, 2026 | 2026-06-22 12:00 | Finished | 8593052 — MediaPipe hand tracking, camera controls, and landmark display.
|  |  | - Check if hands are visible | September 16, 2026 | 2026-06-22 12:00 | Finished | 8593052 — MediaPipe hand tracking, camera controls, and landmark display.
|  |  | - Show hand visibility status | September 16, 2026 | 2026-06-22 12:00 | Finished | 8593052 — MediaPipe hand tracking, camera controls, and landmark display.
|  |  | - Display prompt when hands are not detected | September 16, 2026 | 2026-06-22 12:00 | Finished | 8593052 — MediaPipe hand tracking, camera controls, and landmark display.
|  |  | Selected Makaton Hand Gesture Recognition | September 17, 2026 | 2026-09-04 12:00 | Finished | 9fba95c — Trained gesture model artifact and browser runtime weights.
|  |  | - Select target Makaton hand gesture | September 17, 2026 | 2026-06-23 12:00 | Finished | 7390d84 — Real-time gesture prediction and label mapping.
|  |  | - Start Makaton hand gesture recognition attempt | September 17, 2026 | 2026-09-04 12:00 | Finished | 9fba95c — Trained gesture model artifact and browser runtime weights.
|  |  | - Process hand landmark sequence using the selected Makaton hand gesture recognition model | September 17, 2026 | 2026-09-04 12:00 | Finished | 9fba95c — Trained gesture model artifact and browser runtime weights.
|  |  | Gesture Recognition Result Display | September 18, 2026 | 2026-09-17 12:00 | Finished | fa11da1 — Guided gesture-recognition session and retry flow.
|  |  | - Display recognized gesture result | September 18, 2026 | 2026-09-04 12:00 | Finished | 9fba95c — Trained gesture model artifact and browser runtime weights.
|  |  | - Display correct result | September 18, 2026 | 2026-09-04 12:00 | Finished | 9fba95c — Trained gesture model artifact and browser runtime weights.
|  |  | - Display no hand detected result | September 18, 2026 | 2026-06-22 12:00 | Finished | 8593052 — MediaPipe hand tracking, camera controls, and landmark display.
|  |  | - Reset recognition result | September 18, 2026 | 2026-09-17 12:00 | Finished | fa11da1 — Guided gesture-recognition session and retry flow.
|  |  | LLM-Based Corrective Feedback Panel | September 20, 2026 | 2026-09-14 12:00 | Finished | b9f9cd1 — Corrective-feedback API, safeguards, and local fallback.
|  |  | - Generate corrective feedback based on gesture recognition results | September 19, 2026 | 2026-09-14 12:00 | Finished | b9f9cd1 — Corrective-feedback API, safeguards, and local fallback.
|  |  | - Display learner-friendly feedback | September 20, 2026 | 2026-09-14 12:00 | Finished | b9f9cd1 — Corrective-feedback API, safeguards, and local fallback.
|  |  | - Display teacher next-step guidance | September 20, 2026 | 2026-09-14 12:00 | Finished | b9f9cd1 — Corrective-feedback API, safeguards, and local fallback.
| To design, develop, and evaluate a tailored web-based learning facility and content management platform for SPED teachers that will assist in managing and delivering organized and structured Makaton learning instruction. | Implementation of Account Management Module - Login for Teachers and Admins - Account Settings and Profile Management - Teacher Account Management - Admin Content Oversight Implementation of Makaton Learning Content Management Module - Multimedia Content for Demonstration of Makaton Symbols, Gestures, and Speech - Makaton Symbol Card Repository - Upload and Edit of Makaton Symbol Cards - Makaton Content Category Filter - Lesson Management | ACCOUNT MANAGEMENT AND MAKATON LEARNING CONTENT MANAGEMENT MODULES | August 31, 2026 | 2026-09-17 12:00 | Finished | Latest required child evidence: 554dbd1 — Lesson editor freeze fixed.
|  |  | Login for Teachers and Admins | August 25, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Login with teacher account | August 25, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Login with administrator account | August 25, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Redirect users by role | August 25, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Apply security for authenticated routes | August 25, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | Account Settings and Profile Management | August 26, 2026 | 2026-09-14 12:00 | Finished | ec0365c — Separate profile page and profile menu.
|  |  | - View profile settings | August 26, 2026 | 2026-09-14 12:00 | Finished | ec0365c — Separate profile page and profile menu.
|  |  | - Update profile details | August 26, 2026 | 2026-09-14 12:00 | Finished | ec0365c — Separate profile page and profile menu.
|  |  | - Manage password section | August 26, 2026 | 2026-09-14 12:00 | Finished | ec0365c — Separate profile page and profile menu.
|  |  | - Manage accessibility settings | August 26, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | Teacher Account Management | August 27, 2026 | 2026-09-15 12:00 | Finished | 341f379 — Admin account/role controls and Settings redesign.
|  |  | - View teacher accounts | August 27, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Change teacher role | August 27, 2026 | 2026-09-15 12:00 | Finished | 341f379 — Admin account/role controls and Settings redesign.
|  |  | - Deactivate teacher account | August 27, 2026 | 2026-09-03 12:00 | Finished | aa7d392 — Database-only records and shared-activity permissions.
|  |  | - Reactivate teacher account | August 27, 2026 | 2026-09-03 12:00 | Finished | aa7d392 — Database-only records and shared-activity permissions.
|  |  | Admin Content Oversight | August 27, 2026 | 2026-09-15 12:00 | Finished | 341f379 — Admin account/role controls and Settings redesign.
|  |  | - View system overview | August 27, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - View all learning content | August 27, 2026 | 2026-09-15 12:00 | Finished | 341f379 — Admin account/role controls and Settings redesign.
|  |  | - View uploaded media | August 27, 2026 | 2026-09-15 12:00 | Finished | 341f379 — Admin account/role controls and Settings redesign.
|  |  | - View activity and content logs | August 27, 2026 | 2026-09-15 12:00 | Finished | 341f379 — Admin account/role controls and Settings redesign.
|  |  | Multimedia Content for Demonstration of Makaton Symbols, Gestures, and Speech | August 28, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Add Makaton/PECS learning content | August 28, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Add gesture learning content | August 28, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Upload symbol image files | August 28, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Upload gesture image or video files | August 28, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Upload audio files | August 28, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - View uploaded media | August 28, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | Makaton Symbol Card Repository | August 29, 2026 | 2026-09-17 12:00 | Finished | 9ff624e — Content search corrected to label-only.
|  |  | - View symbol card repository | August 29, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - Search symbol cards | August 29, 2026 | 2026-09-17 12:00 | Finished | 9ff624e — Content search corrected to label-only.
|  |  | - Filter cards by category | August 29, 2026 | 2026-06-26 12:00 | Finished | 6c2af87 — Symbol playground, audio playback, and MSAV validation.
|  |  | - View symbol card details | August 29, 2026 | 2026-09-15 12:00 | Finished | 203b73c — Content details, categories, lessons, and media tabs.
|  |  | Upload and Edit of Makaton Symbol Cards | August 29, 2026 | 2026-09-16 12:00 | Finished | d21d819 — Media removal controls and lesson activity/practice link.
|  |  | - Upload symbol card image | August 29, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Upload symbol card audio | August 29, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Edit symbol card label, description, and tags | August 29, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Delete symbol card with confirmation | August 29, 2026 | 2026-09-16 12:00 | Finished | d21d819 — Media removal controls and lesson activity/practice link.
|  |  | Makaton Content Category Filter | August 30, 2026 | 2026-09-02 12:00 | Finished | b92cffe — Category editor and database functions.
|  |  | - View content categories | August 30, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Create content category | August 30, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Edit content category | August 30, 2026 | 2026-09-02 12:00 | Finished | b92cffe — Category editor and database functions.
|  |  | - Filter learning items by category | August 30, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | Lesson Management | August 31, 2026 | 2026-09-17 12:00 | Finished | 554dbd1 — Lesson editor freeze fixed.
|  |  | - View lesson list | August 31, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Create manual lesson | August 31, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Generate lesson from learning item | August 31, 2026 | 2026-06-18 12:00 | Finished | d4f31d7 — Supabase Auth, database, Storage, and route middleware.
|  |  | - Edit draft lesson before saving | August 31, 2026 | 2026-09-17 12:00 | Finished | 554dbd1 — Lesson editor freeze fixed.
|  |  | - Open related activity or practice action | August 31, 2026 | 2026-09-16 12:00 | Finished | d21d819 — Media removal controls and lesson activity/practice link.
Prepared By:
Lugue, Julian Matthew O. | Oñate, James Gabrielle G. | Perez, Lloyd Raphael M.
Approved By:
Dennis A. Martillano

## Progress
Feature Completion Tracker
Overview of feature readiness per module
|  | Total Features | Done (OK) | Pending | Overall %
|  | 107 | 39 | 68 | 36.45%
# | Objectives | Scope | Module | Total Features | Done (OK) | % Complete | Status | Notes
1 | Main Objective | Overall MakaLearn System | Account Management | 2 | 2 | 100% | Complete
2 |  |  | Learning Content Management | 2 | 2 | 0% | Not Started
3 |  |  | Symbol Playground & Activities | 3 | 3 | 0% | Not Started
4 |  |  | Gesture + LLM Feedback | 3 | 2 | 0% | Not Started
5 | Objective 1 | Symbol Exploration | Symbol Exploration Playground | 5 | 5 | 0% | Not Started
6 |  | Interactive Symbol Activities | Activity Creation & Drafting | 4 | 4 | 0% | Not Started
7 |  |  | Activity Library & Player | 4 | 4 | 0% | Not Started |  | Objective Completion Tracker
8 |  |  | Drag-and-Drop Activity | 5 | 4 | 0% | Not Started |  | Overview of objective readiness
9 |  |  | Matching-Type Activity | 4 | 4 | 0% | Not Started
10 |  |  | Fill-in-the-Blank Activity | 5 | 4 | 0% | Not Started |  |  | Total Objective | Done (OK) | Pending | Overall %
11 |  | Symbol Audio Playback | Symbol Audio Playback | 3 | 3 | 0% | Not Started |  |  | 4 | 1 | 3 | 25%
12 |  | MSAV Validation | MSAV Arrangement Validation | 2 | 2 | 0% | Not Started
13 | Objective 2 | Camera-Based Gesture Practice | Camera Display | 4 | 4 | 0% | Not Started |  | # | Objectives | Total Scope | Done (OK) | % Complete | Status | Notes
14 |  |  | Gesture Reference Panel | 4 | 4 | 0% | Not Started |  | 1 | Main Objective | 4 | 1 | 25% | In Progress
15 |  |  | Hand Visibility Indicator | 3 | 3 | 0% | Not Started |  | 2 | Objective 1 | 4 | 0 | 0% | Not Started
16 |  |  | Selected Gesture Recognition | 3 | 3 | 0% | Not Started |  | 3 | Objective 2 | 3 | 0 | 0% | Not Started
17 |  |  | Recognition Result Display | 4 | 4 | 0% | Not Started |  | 4 | Objective 3 | 9 | 9 | 100% | Complete
18 |  | Gesture Recognition Model | Gesture Model Development | 5 | 1 | 0% | Not Started |  | TOTAL |  | 20 | 9 | 45%
19 |  | LLM Corrective Feedback | Corrective Feedback Panel | 3 | 3 | 0% | Not Started
20 | Objective 3 | Teacher/Admin Login | Teacher/Admin Login | 4 | 4 | 100% | Complete |  | Scope Completion Tracker
21 |  | Account Settings & Profile | Profile & Settings Management | 4 | 4 | 100% | Complete |  | Overview of scope readiness
22 |  | Teacher Account Management | Teacher Account Management | 4 | 4 | 100% | Complete
23 |  | Admin Content Oversight | Admin Content Oversight | 4 | 4 | 100% | Complete |  |  | Total Scopes | Done (OK) | Pending | Overall %
24 |  | Multimedia Makaton Content | Multimedia Content Management | 6 | 6 | 100% | Complete |  |  | 4 | 2 | 2 | 40.21%
25 |  | Symbol Card Repository | Makaton Symbol Card Repository | 4 | 4 | 100% | Complete
26 |  | Symbol Card Upload & Edit | Symbol Card Upload & Edit | 4 | 4 | 100% | Complete |  | # | Scopes | Total Features | Done (OK) | % Complete | Status | Notes
27 |  | Content Category Filter | Category Management | 4 | 4 | 100% | Complete |  | 1 | Account Management | 16 | 16 | 100% | Complete
28 |  | Lesson Management | Lesson Management | 5 | 5 | 100% | Complete |  | 2 | Learning Content Management | 23 | 23 | 100% | Complete
TOTAL |  |  |  | 107 | 39 | 36.45% | In Progress |  | 3 | Makaton Symbol Playground & Activity | 32 | 0 | 0% | Not Started
[9 empty] | 4 | Makaton Gesture Recognition & LLM Feedback | 26 | 0 | 0% | Not Started
[9 empty] | TOTAL |  | 97 | 39 | 40.21%

## Sample 1
FITNESS BUDDY
1 | Getting Started | Create your account, log in, and set up your profile
2 | The Dashboard | Understand your home screen, BMI card, progress ring, and menu
3 | Training Program | Build your weekly workout plan and browse the exercise library
4 | Starting a Workout | Launch a live session, track reps/time, and use the GPS map
5 | After Your Workout | Save your session stats and attach progress photos
6 | Progress & Analytics | Read your charts, switch metrics, and view fitness trends
7 | AI Fitness Chatbot | Ask the AI for advice, get personalised cardio guidance
8 | Social & Community | Join the Feed, create Groups, and climb the Leaderboard
9 | Rewards & Achievements | Unlock badges, spend coins in the shop, and customise avatar
10 | Profile & Settings | Edit your profile, manage notifications, and privacy options
01 · Getting Started
# | What to do | Tap / Press this | What you will see | Tip / Note
FIRST LAUNCH
1 | Open the app | Tap the Fitness Buddy icon on your home screen | The splash screen with the Fitness Buddy logo. If you have logged in before, you will be sent straight to the Dashboard after 1.5 seconds. | If you see the Dashboard immediately, your session is still active — no need to log in again.
2 | Start the sign-up process | Tap the 'Get Started' button | The Login screen opens with fields for email and password.
NEW USER — CREATE AN ACCOUNT
3 | Go to the Sign Up screen | Tap 'Sign Up' at the bottom of the Login screen | The Sign Up screen with an Email field and a Password field.
4 | Enter your email | Tap the Email field and type your email address | Your email appears in the field. | Use a valid email — you will need it to reset your password later.
5 | Enter a password | Tap the Password field and type a password | Password is hidden behind dots. | Firebase requires a minimum of 6 characters. Use a mix of letters and numbers.
6 | Create your account | Tap the 'Sign Up' button | Account is created and the app moves to the Setup Profile wizard. | If you see a red error toast, the email may already be in use — try a different one.
RETURNING USER — LOG IN
3* | Log in to your account | Enter your email and password, then tap 'Login' | If correct, you are taken directly to the Dashboard. If incorrect, a Toast error message appears. | Tap 'Reset Password' in Settings if you have forgotten your password.
SETUP PROFILE WIZARD (5 pages — tap Continue to advance)
7 | Page 1 — Personal Info | Fill in: Full Name, Username (@handle), Bio (optional). Tap 'Continue' | Progress bar advances to 20%. Page 2 slides in. | Your username will appear on the Leaderboard and Community Feed.
8 | Page 2 — Body Metrics | Fill in: Age, Weight (kg), Height (cm), Target Weight (kg). Tap 'Continue' | Progress bar moves to 40%. Page 3 slides in. | These values are used to calculate your BMI and calorie estimates.
9 | Page 3 — Fitness Goals | Fill in: Daily Step Goal, Daily Calorie Goal, Active Minutes Goal. Tap 'Continue' | Progress bar moves to 60%. Page 4 slides in. | A good starting step goal is 8,000 steps per day for beginners.
10 | Page 4 — Workout Days | Tap the day chips to select days (Mon–Sun). Tap 'Continue' | Selected day chips highlight. Progress bar moves to 80%. | These days are highlighted on your Training Program calendar.
11 | Page 5 — Activity Level | Tap the Activity Level spinner, choose a level, tap 'Finish & Start' | Button briefly shows 'Saving…' then takes you to the Dashboard. | Be honest — this helps the AI Chatbot give you accurate cardio guidance.
02 · The Dashboard
# | What to do | Tap / Press this | What you will see | Tip / Note
READING YOUR DASHBOARD
1 | Open the Dashboard | Tap the Home icon (house) in the bottom navigation bar | The main Dashboard screen with your name, BMI card, and activity ring. | The Dashboard updates in real time — data refreshes every time Firebase sends new information.
2 | Check your BMI status | Look at the BMI card at the top of the screen | Your BMI number and a status label (e.g. 'Healthy', 'Overweight'). | BMI is calculated from the weight and height you entered during setup.
3 | Check your daily progress | Look at the circular activity ring and horizontal progress bar | A percentage and text showing steps to next milestone. | When you reach your step goal, the ring fills completely and shows 'Milestone reached! 🏆'.
4 | View recent achievements | Scroll down to the achievements list | A horizontal list of up to 5 recent achievement badges you have earned. | Tap an achievement to see full details in the Achievements screen.
NAVIGATING THE APP
5 | Use the bottom navigation bar | Tap any of the 5 icons: Dumbbell · Robot · House · Chart · People | The selected screen opens. The tapped icon turns the primary brand colour. | The nav bar stays visible on every main screen.
6 | Open the side menu | Tap the hamburger icon (≡) in the top-right of the header bar | A popup menu: Edit Profile · Settings · Logout. | Edit Profile' opens Health Metrics in edit mode.
7 | Edit your health data | Tap 'Edit Profile' in the side menu | The Health Metrics screen opens pre-filled. Update and tap 'Update Data'. | Update your weight regularly — keeps your BMI and calorie estimates accurate.
8 | Log out | Tap the hamburger menu (≡) → tap 'Logout' | You are signed out and returned to the Login screen. | Your data is saved in Firebase — logging out does not delete anything.
03 · Training Program
# | What to do | Tap / Press this | What you will see | Tip / Note
OPENING THE TRAINING PROGRAM
1 | Open Training Program | Tap the Dumbbell icon in the bottom navigation bar | The Training Program screen with a date header and a horizontal calendar.
USING THE CALENDAR
2 | Navigate the week calendar | Swipe left or right on the calendar row | The calendar snaps in 7-day week blocks spanning 2 years (104 weeks total). | The calendar jumps to the nearest Sunday boundary — this is intentional.
3 | Select a specific day | Tap any day tile in the calendar row | The selected day tile highlights. The exercise list updates for that day. | Tap today's date to return to the current day's schedule.
ADDING EXERCISES TO YOUR PLAN
4 | Add an exercise to a date | Select the target date, then tap the blue '+' floating action button | The Exercise Library opens in Selection Mode. | The selected date is passed to the Library — exercises you pick will be assigned to that day.
5 | Choose an exercise from the Library | Tap any exercise card in the Library | The Exercise Description screen opens showing name, category, intensity, equipment, and demo image.
6 | Add the exercise to your plan | Tap 'Add to Calendar' on the Exercise Description screen | You are returned to Training Program. The exercise now appears for the selected date. | You can add as many exercises as you like to one day.
7 | Delete an exercise from the plan | Swipe the exercise row to the left | A delete action is revealed. The row is removed and deleted from Firebase. | This only removes the exercise from that date — it does not delete it from the Library.
BROWSING THE EXERCISE LIBRARY
8 | Browse all exercises | Tap the 'Exercise Library' button | The full Exercise Library opens in Browse Mode with all cardio exercises. | In Browse Mode, tapping an exercise opens its details — no exercise will be added to your plan.
9 | Search for an exercise | Tap the search bar and type a keyword (e.g. 'jump rope', 'cycling') | The list filters in real time to show only matching exercises. | You can search by exercise name or category name.
10 | Filter by category or intensity | Tap the Filter icon → select chips → tap 'Apply' | The exercise list updates to show only matching exercises. | Tap 'Reset' in the filter sheet to clear all filters.
11 | Read an exercise description | Tap any exercise card | Exercise Description screen shows: Name, category, intensity badge, equipment, tracking type, demo image. | Tracking Type' tells you how the live session will log this exercise.
04 · Starting a Workout
# | What to do | Tap / Press this | What you will see | Tip / Note
STARTING A SESSION
1 | Launch a workout from your plan | In Training Program, tap an exercise → tap 'Start Exercise' | The Live Exercise Session screen opens with two tabs: Stats and a dynamic tool tab. | The tab label changes based on the exercise type set in the Library.
TAB 1 — STATS (always visible)
2 | Monitor your live stats | Keep 'Stats' tab selected (default) | Four live counters: Steps · Timer · Distance · Calories. | The step counter uses your phone's built-in sensor. Keep the phone in your pocket or hand.
3 | Start / pause the timer | Tap the Start button in the Stats area | Timer begins counting up. Tap again to pause. | Steps are counted whether the timer is running or not.
TAB 2 — DYNAMIC TOOL (changes by exercise type)
4 | LOG SETS & REPS (Sets & Reps type) | Tap the 'Log' tab → enter Weight and Reps → tap '+ Add Set' | Each set is saved in a scrollable list showing set number, weight, and reps. | You can log as many sets as needed. Sets are saved even if you navigate back to Stats.
5 | TIMER COUNTDOWN (Duration Only type) | Tap the 'Timer' tab → set target duration → tap 'Start Set' | A large countdown timer runs. A notification sounds when it reaches zero. | Tap 'Add Set' after each interval to log multiple timed sets.
6 | GPS MAP ROUTE (GPS / Outdoor type) | Tap the 'Map' tab → grant location permission → tap 'Start Recording' | Your location appears on the map. A blue polyline traces your route in real time. | Stay outside with a clear sky for the most accurate GPS signal.
7 | SIMPLE COMPLETION CHECK (Simple Check type) | Tap the 'Done' tab → tap the checkmark when finished | A confirmation that the exercise has been marked complete. | Used for stretching or warm-up routines where tracking numbers is not needed.
FINISHING YOUR WORKOUT
8 | End the session | Tap 'Finish Workout' | The app compiles all data and automatically opens the Post-Workout Summary screen. | Do not close the app before tapping 'Finish Workout' — unsaved data will be lost.
05 · After Your Workout
# | What to do | Tap / Press this | What you will see | Tip / Note
REVIEWING YOUR RESULTS
1 | View your session summary | This screen opens automatically after you tap 'Finish Workout' | A summary card: Exercise image or GPS map · Total Work · Average Level · Intensity · Active Time · Fastest Set. | Stats depend on exercise type — GPS shows distance/pace; strength shows volume/intensity.
2 | Understand each metric | Read the summary cards on screen | Total Work · Intensity · Active Time · Fastest Set — each defined on-screen. | These metrics are calculated from the sets and times logged during the live session.
ADDING PHOTOS
3 | Attach a progress photo (optional) | Tap the photo add button / camera icon in the photo section | Your phone's photo picker opens. You can select up to 5 photos. | Photos are compressed and saved alongside your workout data in Firebase.
4 | Remove a photo before saving | Tap the × button on any photo thumbnail | The photo is removed from the selection list. | You cannot add photos after saving — make your selection before tapping 'Save Workout'.
SAVING OR DISCARDING
5 | Save your workout | Tap 'Save Workout' | A saving indicator appears, then you return to the Dashboard. Your workout is stored in Exercise History. | Saving also awards fitness points, which appear on the Leaderboard.
6 | Discard the session | Tap 'Discard' | A confirmation dialog appears. Tap 'Discard' to confirm, or 'Cancel' to go back. | Discarded sessions do not appear in history and do not award points.
06 · Progress & Analytics
# | What to do | Tap / Press this | What you will see | Tip / Note
OPENING PROGRESS TRACKING
1 | Open Progress Tracking | Tap the Chart icon in the bottom navigation bar | The Progress Tracking screen with a line chart showing your Steps data for the current year.
SWITCHING METRICS AND TIMEFRAMES
2 | Change the metric displayed | Tap one of the three metric buttons: Steps · Minutes · Calories | The chart re-draws to show the selected metric. | Minutes' shows total active minutes per day — a good measure of consistency.
3 | Change the timeframe view | Tap one of the three timeframe buttons: Daily · Weekly · Monthly | The chart re-draws with the new grouping. X-axis labels update to match. | Monthly view is best for spotting long-term trends.
4 | Navigate between years | Tap the '+' or '−' buttons next to the year label | The chart shifts forward or backward one year. | Your full workout history is stored — you can go back to the start of your activity.
5 | Read a specific data point | Tap any bar or point on the chart | A popup label appears showing the exact value and date. | Long-press on the chart to drag the selection across multiple data points.
6 | Share your progress chart | Tap the Share / Export button | The chart is captured as an image and the Android share sheet opens. | Great for sharing your consistency streak with friends or your coach.
DETAILED FITNESS ANALYTICS
7 | Open detailed analytics | Tap the 'Fitness Progress' shortcut from Progress Tracking | The Fitness Progress screen with tabs: GPS Map · Strength · Cardio.
8 | Switch activity type view | Tap the tabs: GPS Map · Strength · Cardio | Stat cards, trend chart, and activity history list all update for the selected category.
9 | Swipe through comparison cards | Swipe left or right on the comparison card section | Side-by-side cards comparing different exercises or time periods. | Use these to identify which exercises you are improving at most.
10 | View your exercise history | Tap the Chart icon → tap 'Exercise History' | A monthly calendar grid highlighting days when you exercised, and a scrollable list below. | Tap '<' and '>' to navigate between months.
07 · AI Fitness Chatbot
# | What to do | Tap / Press this | What you will see | Tip / Note
OPENING THE CHATBOT
1 | Open the AI Chatbot | Tap the Robot icon in the bottom navigation bar | The Chatbot screen. On first visit: 'Kumusta! I am Fitness Buddy. How can we improve your health today?' | Previous conversations are automatically loaded from Firebase — history is preserved between sessions.
CHATTING WITH THE AI
2 | Type your question | Tap the message input field and type your question | Your message appears as a blue bubble on the right side of the chat. | The AI is trained on cardio exercise and NCD topics. Questions outside this domain may not get helpful answers.
3 | Wait for the AI response | (no tap needed — response is automatic) | A 'Fitness Buddy is thinking…' bubble appears, then the AI's response replaces it. | Responses may take 5–15 seconds depending on your internet connection.
4 | Continue the conversation | Type another message and tap Send | The conversation continues. The AI uses previous messages as context. | Ask follow-up questions like 'Can you give me a specific routine?' for more detail.
5 | The AI uses your profile data | (automatic — no action required) | AI answers are personalised using your username, age, BMI, active minutes goal, and health conditions. | Keep your Health Metrics up to date so the AI gives you the most relevant guidance.
MANAGING YOUR CHAT HISTORY
6 | Clear your entire chat history | Tap the 'Clear Chat' button in the top header bar | A confirmation dialog: 'Delete all messages?' — tap 'Clear' to confirm. | Clearing chat is permanent. The AI will start a fresh greeting on your next visit.
7 | Keyboard behaviour | (automatic) | When the keyboard opens, the bottom navigation bar hides automatically. It reappears when dismissed. | Tap anywhere outside the keyboard to dismiss it and restore the nav bar.
08 · Social & Community
# | What to do | Tap / Press this | What you will see | Tip / Note
OPENING THE SOCIAL HUB
1 | Open the Social Hub | Tap the People icon in the bottom navigation bar | The Social screen with three tabs: Feed · Groups · Leaderboard.
COMMUNITY FEED
2 | Browse the community feed | Make sure the 'Feed' tab is selected | A scrollable list of posts: avatar, name, timestamp, caption, optional photo, and like count. | Posts are sorted newest first.
3 | View a full post | Tap anywhere on a post card | The Post Detail screen opens with all photos and a comment/reaction section.
4 | Visit a user's profile | Tap the avatar (emoji circle) on any post | That user's public Profile screen opens with display name, bio, badge, points, and level. | Tap 'Follow' to follow that user.
5 | Create a new post | Tap the '+' floating action button (bottom-right) | A 'Create Post' bottom sheet slides up with caption input, photo attachment, and 'Post' button. | Share a workout milestone, progress photo, or fitness tip.
6 | Submit your post | Type your caption, optionally add a photo, then tap 'Post' | The bottom sheet closes. Your new post appears at the top of the Feed.
GROUPS
7 | Browse or join a group | Tap the 'Groups' tab | Two sub-tabs: 'My Groups' and 'Discover'.
8 | Join an existing group | In the 'Discover' tab, find a group and tap 'Join' | The group moves to your 'My Groups' tab.
9 | Create a new group | Tap the '+' floating button → fill in Group Name, Description, Privacy → tap 'Create' | Your new group appears in 'My Groups'. You are automatically the group Admin. | Public groups are visible in the 'Discover' tab.
10 | Open a group and view tasks | Tap a group card | Group Detail screen shows: Member list · Group feed · Task list with checkboxes.
11 | Add a challenge task (Admin only) | Tap 'Add Task' → fill in name, description, deadline → tap 'Save' | The new task appears in the task list for all group members. | Use tasks to set group challenges like '30-minute walk every day this week'.
12 | Mark a task complete | Tap the checkbox next to a task | The checkbox fills. Your completion status updates for all group members.
LEADERBOARD
13 | View the global rankings | Tap the 'Leaderboard' tab | A podium showing Rank 1, 2, 3 with avatar, name, badge, and points. Below is the full ranked list. | Your own row is highlighted with a 'YOU' tag.
14 | Earn more points | (no tap — points are earned automatically) | Points awarded for: Completing workouts · Unlocking badges · Engaging with community posts. | Consistency is key — saving a workout every day adds up faster than occasional big sessions.
09 · Rewards & Achievements
# | What to do | Tap / Press this | What you will see | Tip / Note
ACHIEVEMENTS
1 | Open Achievements | Tap 'Achievements' from the Dashboard shortcut or the side menu | A grid of badges. Unlocked badges are in full colour. Locked badges are greyed out with a padlock.
2 | Filter badges | Tap one of three filter buttons: All · Unlocked · Locked | The grid updates to show only the filtered results. | Check 'Locked' to see what goals you still need to hit.
3 | Earn badges automatically | (automatic — no action needed) | Badges unlock at milestones: First workout · 7-day streak · 10,000 steps · 100 total workouts. | Each badge award also earns you fitness points.
AVATAR CUSTOMIZATION
4 | Open Avatar Customization | Navigate to Avatar Customization from the Dashboard or rewards area | Your avatar in the preview area. Three tabs: Body · Head · Face. Coin balance shown at top. | The first item in each category is unlocked for free. All others cost coins.
5 | Browse available parts | Tap the Body, Head, or Face tabs. Tap 'ALL' to see all items, or 'UNLOCKED' for what you own. | A grid of avatar parts. Locked items show a coin price overlay.
6 | Unlock a locked item | Tap a locked avatar item | A purchase dialog: 'Unlock [item] for [price] coins?' Tap 'Confirm' to buy. | If you do not have enough coins, a 'Not enough coins' Toast appears.
7 | Equip an item | Tap an unlocked item to select it. Tap 'Save / Equip' | The avatar preview updates immediately to show your new look. | You can mix and match any unlocked Body + Head + Face combination.
8 | Earn coins | (automatic — coins are awarded with workouts and achievements) | Your coin balance (shown at top of Customization screen) increases after each completed workout. | Coins are the in-app currency — the only way to earn them is through the app.
10 · Profile & Settings
# | What to do | Tap / Press this | What you will see | Tip / Note
EDITING YOUR PROFILE
1 | Open Edit Profile | In the Social Hub, tap your own avatar, or navigate to Profile → tap 'Edit Profile' | The Edit Profile screen with your current Display Name, Bio, Avatar, Colour, and Featured Badge.
2 | Change your display name | Tap the Display Name field, clear it, type a new name → tap 'Save' | Your new name appears on your profile, posts, and the Leaderboard. | Display Name is required — the Save button will not work if this field is empty.
3 | Change your bio | Tap the Bio field, edit your text → tap 'Save' | Your new bio appears on your public profile. | Keep it short — it appears below your name on your profile card.
4 | Change your avatar emoji | Tap any emoji in the Avatar grid | The avatar preview circle updates to show the selected emoji.
5 | Change your avatar background colour | Tap any colour swatch in the colour grid | The avatar circle background changes to the selected colour. | Choose a colour that contrasts well with your chosen emoji.
6 | Set a featured badge | Tap any badge in the Featured Badge grid (only unlocked badges are selectable) | The badge preview updates. This badge appears next to your name on profile and Leaderboard. | Unlock more badges through achievements to have more options here.
7 | Save all profile changes | Tap the 'Save' button | A brief saving indicator, then you return to your Profile screen with all changes applied.
APP SETTINGS
8 | Open Settings | Tap the hamburger menu (≡) on the Dashboard → tap 'Settings' | The Settings screen with your username, email (read-only), and toggle switches.
9 | Toggle Workout Reminders | Tap the 'Workout Reminders' switch | Switch turns on (blue) or off (grey). When on, the app sends reminders on your workout days. | Make sure notification permissions are granted for the app in your phone's Settings.
10 | Toggle Inactivity Alerts | Tap the 'Inactivity Alerts' switch | When on, the app notifies you if you have not logged a workout in more than 2 days. | Useful for keeping your streak and motivation going.
11 | Set your profile to Private | Tap the 'Profile Visibility' switch | When Private is on, other users cannot view your profile or see your posts in the community feed. | The Leaderboard still shows your username and points even in Private mode.
12 | Save your settings | Tap 'Save Settings' | Your username update and all toggle states are written to Firebase.
ACCOUNT SECURITY
13 | Reset your password | Tap 'Reset Password' | Firebase sends a password reset email. A Toast confirms: 'Password reset email sent'. | Check your spam folder if the email does not arrive within a few minutes.
14 | Update your health metrics | Tap the hamburger menu (≡) → tap 'Edit Profile' | Health Metrics screen opens in edit mode. Update weight, height, goals, or workout days, then tap 'Update Data'. | Re-calculate your BMI after every significant change in weight.

## Sample 2
How can a mobile health application be designed to provide a platform for Filipino non-gym-goers to overcome specific motivational barriers — lack of time, guidance, and training plan — that prevent them from adhering to a consistent cardiovascular exercise routine? | [Main Objective] Design and develop an adaptive, AI-driven mobile platform for Filipino non-gym-goers that leverages gamified engagement to overcome motivational barriers and deliver personalized cardiovascular training to promote consistent adherence and mitigate NCD risks. | Platform is focused exclusively on cardio-based exercises. Resistance training, strength-based plans, and sports-specific programs are NOT included. ML personalization is limited to user-provided inputs and in-app metrics only (no external wearable IoT sensor integration). | Training Program Module • AI-Generated Adaptive Plans (adjust based on performance history & goals) • Exercise Library with multimedia content • Workout Timer / Session Tracker • Completion Tracking with visual progress milestones Fitness AI Chatbot Module • AI Recommendation Engine (custom suggestions from user data) • Motivational Messaging & adaptive reminders • Integration with Training Program module Progress Tracking Module • Daily, weekly, and monthly trend charts • Statistical summaries (calories burned, active time) • Goal Attainment Monitor Dashboard Module • Performance Overview with dynamic visualizations • Quick Access Shortcuts • Data-driven 'Bits and Tips' section User Customization Module • Profile Configuration (demographics, health metrics, fitness goals) • Notification, reminder, and privacy settings Rewards & Leaderboard Module • Achievement Badges + points/ranking system • Leaderboard Display for friendly competition Group Fitness Challenge Module • Friend System with Performance Comparison • Community Rankings • Team Challenges
| [Objective 1] Implement personalized goal-setting and progress visualization through an interactive cardio activity dashboard to enhance user motivation and engagement. | Dashboard and progress features are driven by user-inputted personal stats (e.g., BMI). Gamification layer (rewards, leaderboards) is included to drive behavioral consistency. | DASHBOARD (MODULE) • Personalized Goal-Setting Module • Intuitive Data Visualizations (progress charts, consistency tracking) • BMI-linked personalized goal display • WHO guideline-aligned progress indicators GAMIFICATION (MODULE) • Reward System (badges, points) • Competitive Leaderboards • Achievement-oriented experience design
| [Objective 2] Provide an Adaptive Training System to generate personalized workout activities and user support, tailored to the user's real-time schedule and activity goal. | Machine learning model analyzes real-time progress, fatigue levels, and overall fitness status to auto-adjust intensity, duration, and type of workout. No human trainer required. | ADAPTIVE TRAINING SYSTEM (MODULE) • ML Algorithm for dynamic cardio plan generation • Real-time adjustment of intensity, duration, and workout type • Fatigue & fitness level analysis AI CHATBOT (MODULE) • Flan-T5 fine-tuned LLM (domain: cardio & NCD) • RAG (Retrieval-Augmented Generation) Architecture • Keyword-based contextual search • Prompt Engineering layer • ROUGE-L evaluation (target F1-score ≥ 84%) • Negation Consistency Check (0% Polarity Violation Rate) • Out-of-domain query rejection (False Positive Rate control) • Gold Standard validation (3 categories: Psychoeducation, Risk Screening, Crisis Intervention)
| [Objective 3] Integrate social elements like Community Rankings to increase user engagement and retention through an interactive and supportive in-app community. | Social ecosystem recreates gym-like accountability structures virtually. Supports peer-to-peer encouragement and collective goal-setting for non-gym-goers. | SOCIAL / COMMUNITY (MODULE) • Friend System (connect with peers) • Workout Group Formation • Community Challenges (collaborative) • Community Rankings display • Team Challenge participation • Peer-to-peer encouragement mechanisms

## Sample 3
Get Started |  | USER CUSTOMIZATION
Signup |  | Signup
Login |  | - Input of Email and Password
CRUD Information |  | Login
Customize Avatar |  | - Input of Email and Password
Home/Dashboard |  | - CRUD Personal Information
Training |  | -- Input of Age, Height, Weight, Target Weight, Target Steps, Minutes per Session, Availability Sched
Calendar |  | - Customize Avatar
Generate AI Plan | -- | -- Allow user to customize their avatar
Exercise | Instructions (Video) | DASHBOARD
Finish Exercise | Specify | - Display Health metrics
Progress Tracking |  | -- BMI, Steps
Home/Dashboard |  | - Leaderboards (Friends)
- Daily Bits n Tips
Current Exercise |  | - Performance Overview
Chart |  | - Current/Next Exercise
Metrics |  | TRAINING
Chatbot |  | - Calendar
-- Day-to-day workout
Home/Dashboard | Friends Leaderboard | - Exercise Library
Bits n Tips | Achievements | -- List of all exercises
Profile |  | --- Video Instructions for each exercise
- Start a new exercise
Edit Profile |  | - Selection of Exercise Type (GPS MAP, DURATION, VOLUME, TIMER REPS, MACHINE INPUT)
Social
Group Challenge |  | Gps Map
- Selection of Goal ( Step Count, Distance, Duration, Calories Burned, Freestyle)
- Stats
- Map (Location)
Duration
- Stats
- Timer (per Set)
Volume
- Stats (Sets)
Timer Reps
- HIIT Configuration (AMRAP and Challenge)
-- AMRAP (Sets, Work Time, Rest Time)
-- Challenge (Sets, Work Time, Rest Time)
- Stats
-- Reps & Time
-- Add/Start/Finish Sets
Machine Input
- Stats
-- Machine Session
-- Enable/Disable Rest Timer
-- Add/Start/Finish Sets
CHATBOT
- User would be able to see Chat History
- Delete Chat History
- Chat with AI

## Sample 4
Step by the Step
Sign Up | Sign Up
Login | - Username and Password
Dashboard
- Recent Activities | Login
- Bits n Tips | - Username and Password
- Achievements | - User personal information for first time login
- Daily Goal Tracking
- Leaderboard | Dashboard
- Start New Activity | - Recent activities (Recent workouts done and progress)
- Achievements (Display badges, progress, recently achieved)
Training Program | - Leaderboard (Display Top Leaderboard or Current Leaderboard Ranking)
- Daily Summary of Workout | - Start New Activity (Redirects to starting another workout)
- Workout Library
AI Chatbot | Training Program
- User Input and Chatbot Response | - Based on user information ai plan would be given; user can customize their own plan
Progress Tracking | - Day to day summary of what workouts are done and to be completed
- Activity History | - Workout Library (Display all available workout)
- Performance History / Summary
- Goal Attainment Monitor | Progress Tracking
Social | - Activity History (Statistic about each activity done)
- Friend System | - Performance History (Weekly Monthly and Yearly)
- User Feed | - Goal Attainment (For users to see if they are still on track
- Group Fitness Challenge
- Friend Profile | Social
- Friend System (User can add one another)
- User Feed (User can share, ask, interact about anything)
- Group Fitness Challenge (Shared goal attainment within on circle)

## Sample 5
Problem Statement | Objectives | Scopes | Features | Remarks
How can a mobile health application be designed to provide a platform for Filipino non-gym-goers to overcome the specific motivational barriers, such as lack of time, guidance, and training plan, that prevent them from adhering to a consistent cardiovascular exercise routine? | Main Objective: Design and develop an adaptive, AI-driven mobile platform for Filipino non-gym-goers to overcome motivational barriers and deliver personalized cardio training. | Implementation of Personalized Goal-Setting Structure for planning and monitoring fitness routines aligned with WHO guidelines. | DASHBOARD (MODULE)
- Workout Progress
- Summary of Performance
- Health Bits n Tips
REWARDS & LEADERBOARD (MODULE)
Display Achievements
- Display Recent 5 Achievements
- Display Achievement Title
- Display Achievement Details
- Display Date of Acquisition
Display Leaderboard
- Display Current Leaderboard Placement
| Objective 1: Implement personalized goal-setting and progress visualization through an interactive dashboard. | Implementation of Progress Tracking Analyzing user metrics (like BMI) to generate impactful, accurate progress visualizations. | PROGRESS TRACKING (MODULE)
Display Trend Charts
- Daily, Weekly and Monthly
| Objective 2: Provide an Adaptive Training System to generate personalized workout activities tailored to real-time schedules. | Deployment of Machine Learning Algorithm A fully adaptive plan that adjusts intensity and duration based on fatigue and performance history. | TRAINING PROGRAM (MODULE)
- AI-Generated Adaptive Plans
- Exercise Library (Multimedia)
- Workout Timer & Session Tracker
| Objective 3: Provide real-time, context-based hints and guidance via an AI companion. | Implementation of AI-Enabled Companion Powered by a curated knowledge base to deliver instant feedback and training advice. | FITNESS AI CHATBOT (MODULE)
AI Chatbot
- AI Assistant (User Input, Chatbot Response)
- Adaptive Reminders.
| Objective 4: Integrate social elements to increase engagement and retention through a supportive community. | Implementation of Social Ecosystem Recreating gym dynamics via localized peer connections and collaborative challenges. | GROUP FITNESS (MODULE)
- Friend System & Performance Comparison
- Community Rankings
- Team Challenges.

## Copy of For Checking
User Customization
Get Started
SignUp | SignUp (Email, Password)
| Next Step Button | The Basics (Age, Height) Weight Goals (Weight, Target Weight) Step Goals (step sister) Schedule (Select Days, Minute per Session) Final Review (Remarks) |  |  | Move "The Basics, Weight Goals..." to First-time Login
| Avatar Customization | Customize Avatar Final Review
SignIn | Login (Username, Password)
Login Button
Login
Home | Dashboard |  | Activity (Daily Goal Progress) Bits n Tips (Daily Bits n Tips) Achievement (List of achievements and Progresses) Leaderboard (Top 10) | Three-line Menu | Edit Profile (The Basics, Weight Goals, Step Goals, Schedule) Settings Logout
Training | Calendar | Activities per Day
| AI Plan Button | AI Generated Workout
| Library | Search Filter Activities (Description)
| Add Workout | Search Filter Activities (Description, Add to Calendar Button)
| Activities | Description
|  | Start Exercise | Stats (Distance, Etc.) Timer (Stopwatch, Set Buttons) Finish Exercise
Chatbot | Clear Conversation
| Chat Interface | Chat Box (Type, Send) Chat History (User Prompts, Machine Feedback)
Progress | Charts (Daily, Weekly, Monthly)
Statistical Summary of Metrics
Goal Attainment Monitor
Social & Group Fitness Challenge
Avatar

## Sheet1
Problem Statement | Objectives | Scopes | Features | Features | Remarks
How can a mobile health application be designed to provide a platform for Filipino non-gym-goers to overcome the specific motivational barriers, such as lack of time, guidance, and training plan, that prevent them from adhering to a consistent cardiovascular exercise routine? | Main Objective: The primary objective of this study is to design and develop an adaptive, AI-driven mobile platform for Filipino non-gym-goers, which leverages gamified engagement to overcome specific motivational barriers (lack of time, guidance, and planning) and deliver personalized cardiovascular training to promote consistent adherence and mitigate NCD risks. | Implementation of Dashboard Implementation of Rewards and Leaderboard Implementation of User Customization | Dashboard
|  |  | Fitness Data Management (BMI, calories burned, steps taken, active minutes) | Display Current / Next Activity Progress in Dashboard
Display Daily AI Generated Tips
|  |  | Leaderboard Data Management (Current placement, challenges won) | Display Leaderboard in Dashboard
|  |  | Workout Data Management (Top exercises) | Display Top Exercises in Dashboard
Rewards and Leaderboard
|  |  | Achievement Badge System | Achievement Unlocked
View Achievements (All, Locked, Unlocked)
View Achievement Details (Locked, Unlocked)
Show Achievements in Dashboard (Recently Unlocked / Close to Unlocking)
Show Unlocked Achievement in Social Feed
Show Achievements in User Profile (Own Profile, Friends Profile)
CRUD Achievements Displayed
Show Achievement That Can be Unlocked From Particular Activity / Challenge
|  |  | Leaderboard System | View Friend Leaderboard Through Dashboard (Allow Several Categories
View Leaderboard in Group Fitness Challenge
User Customization
|  |  | Avatar Customization | View Current Avatar in Profile
See Avatar in Dashboard
Select / Update User Avatar
| Objective 1: Implement personalized goal-setting and progress visualization through an interactive cardio activity dashboard to enhance user motivation and engagement. | Implementation of Progress Tracking Implementation of User Customization | Progress Tracking
|  |  | Workout Logs / Activity Reports(Daily, weekly, monthly progress report) | Progress Report Daily, Weekly, Monthly)
Track Fitness Goal (Step Count, Exercise Time, etc)
View Calculated BMI Status (Auto-updated based on weight inputs)
See Fitness Goal Progress Bar in Dashboard
See Activity History From Progress Report
Show Completed Activities in Activity History
Show Details of Completed Activities
|  |  | Export and Share Feature | Share Progress Report to Feed or Outside Apps
|  |  | Data Visualization for Performance Trends | Show Graphs and Charts for Progress Reports
Show Graphs and Charts for Individual Activities / Challenges
User Customization
|  |  | Account Management (Settings) | CRUD Account Information (Username, Email, Password)
Manage Notification Settings (Workout Reminders, Inactivity Alerts)
Manage Privacy Settings (Profile Visibility)
Logout / Deactivate Account
|  |  | Personal Fitness Information | CRUD Health Metrics (Age, Height, Current Weight)
CRUD Fitnness Goals (Target Weight, Descired Activity Level)
| Objective 2: Provide an Adaptive Training System to generate personalized workout activities and user support, tailored to the user's real-time schedule and activity goal. | Implementation of Training Program Implementation of AI Chatbot | Training Program
|  |  | Exercise Library (Instructional Videos) | See Exercise Library Through Training Program
See Selection of Exercises
Filter Exercise Selection
Search Through Exercise Selection
Show Exercise Details (Description, Video, Calories, Time, Difficulty)
|  |  | Workout Calendar Scheduler | See Calendar in Training Program
See Different Workouts For Each Selected Date
CRUD Workout Calendar
Ask AI For Updated Workout Calendar
|  |  | Workout Tracker and Timer | See in Exercises
Timer (Start, Pause, Finish)
Show Details in Timer (Steps, Distance, Pace, etc)
|  |  | AI-Generated Adaptive Workout Plan and Recommendations | Generate Adaptive Workout
Display Recommendations After Workout
AI Chatbot
|  |  | Chat Interface | Open / Close AI Chat Window
Input Text Queries (Natural Language Questions)
Display AI Generated Responses
View Chat Session History
Clear Chat History
|  |  | ML Chatbot Model | Receive Content-Aware Responses (Tailored to user's track data/profile)
Receive NCD-Specific Guidance
Display Safety Warnings / Rejections (If query is medically unsafe or out of scope)
|  |  | Personalized Assistance | Receive Motivational Responses
| Objective 3: Integrate social elements like Community Rankings to increase user engagement and retention through interactive and supportive in-app community. | Implementation of Group Fitness Challenge | Group Fitness Challenge
|  |  | Friend System | Search for Users
CRUD Friend Requests (Send, Accept, Reject, Cancel)
View Friend List
View Friend Profile (Achievements, Avatar, Basic Stats)
|  |  | Team Challenges | View Available / Ongoing Group Challenges
Create Join / Leave Group Challenge
View Team Progress (Collective Steps, Distance, etc.)
View Challenge Rules and Duration
See Current Group Fitness Challenge on Dashboard
|  |  | Community Rankings | View Community Leaderboard
Filter Leaderboard Views (Group Fitness Challenge Only)
|  |  | Performance Comparison | Stat Comparison with other Group
View Personal Rank in Group Leaderboard

## In Order
Problem Statement | Objectives | Scopes | Features | Features | Remarks
How can a mobile health application be designed to provide a platform for Filipino non-gym-goers to overcome the specific motivational barriers, such as lack of time, guidance, and training plan, that prevent them from adhering to a consistent cardiovascular exercise routine? | Main Objective: The primary objective of this study is to design and develop an adaptive, AI-driven mobile platform for Filipino non-gym-goers, which leverages gamified engagement to overcome specific motivational barriers (lack of time, guidance, and planning) and deliver personalized cardiovascular training to promote consistent adherence and mitigate NCD risks. | Implementation of Dashboard Implementation of Rewards and Leaderboard Implementation of User Customization | User Customization
|  |  | Account Management (Settings) | Signup (Email, Password, The Basics, Weight Goals, Step Goals, Availability Schedule, Final Review) | Move The Basics, Weight Goals, Step Goals, Availability Schedule, Final Review to First time Login
Login
Personal Information
Training Program
|  |  | Exercise Library (Instructional Videos) | See Exercise Library Through Training Program
See Selection of Exercises
Filter Exercise Selection
Search Through Exercise Selection
Show Exercise Details (Description, Video, Calories, Time, Difficulty)
See Calendar in Training Program
CRUD Workout Calendar
Start Exercise
Exercise Progress (GPS, Machine Input, Duration,Timer Reps, Volume Distance)
Finish Exercise (Summary, Add Description, Images, Etc.)
See Finished Exercise in Calendar
Dashboard
|  |  | Fitness Data Management (BMI, calories burned, steps taken, active minutes) | Display Current / Next Activity Progress in Dashboard
Display Daily AI Generated Tips
|  |  | Leaderboard Data Management (Current placement, challenges won) | Display Leaderboard in Dashboard
|  |  | Workout Data Management (Top exercises) | Display Top Exercises in Dashboard
Rewards and Leaderboard
Achievement Unlocked Notification
View Achievement Details
View Achievements (All, Locked, Unlocked)
CRUD Account Information (Username, Email, Password)
Manage Notification Settings (Workout Reminders, Inactivity Alerts)
Manage Privacy Settings (Profile Visibility)
Logout / Deactivate Account
|  |  | Personal Fitness Information | CRUD Health Metrics (Age, Height, Current Weight)
CRUD Fitnness Goals (Target Weight, Descired Activity Level)
|  |  | Avatar Customization | View Current Avatar in Profile
See Avatar in Dashboard
Select / Update User Avatar
Training Program
Exercise Library (Instructional Videos)
Workout Calendar Scheduler
Workout Tracker and Timer
| Objective 1: Implement personalized goal-setting and progress visualization through an interactive cardio activity dashboard to enhance user motivation and engagement. | Implementation of Progress Tracking Implementation of User Customization
|  |  | AI-Generated Adaptive Workout Plan and Recommendations | Generate Adaptive Workout
Display Recommendations After Workout
Progress Tracking
|  |  | Workout Logs / Activity Reports(Daily, weekly, monthly progress report) | Progress Report Daily, Weekly, Monthly)
Track Fitness Goal (Step Count, Exercise Time, etc)
View Calculated BMI Status (Auto-updated based on weight inputs)
See Fitness Goal Progress Bar in Dashboard
See Activity History From Progress Report
Show Completed Activities in Activity History
Show Details of Completed Activities
|  |  | Export and Share Feature | Share Progress Report to Feed or Outside Apps
|  |  | Data Visualization for Performance Trends | Show Graphs and Charts for Progress Reports
Show Graphs and Charts for Individual Activities / Challenges
Rewards and Leaderboard
|  |  | Achievement Badge System | Achievement Unlocked
View Achievements (All, Locked, Unlocked)
View Achievement Details (Locked, Unlocked)
Show Achievements in Dashboard (Recently Unlocked / Close to Unlocking)
Show Unlocked Achievement in Social Feed
Show Achievements in User Profile (Own Profile, Friends Profile)
CRUD Achievements Displayed
| Objective 2: Provide an Adaptive Training System to generate personalized workout activities and user support, tailored to the user's real-time schedule and activity goal. | Implementation of Training Program Implementation of AI Chatbot |  | Show Achievement That Can be Unlocked From Particular Activity / Challenge
AI Chatbot
|  |  | Chat Interface | Open / Close AI Chat Window
Input Text Queries (Natural Language Questions)
Display AI Generated Responses
View Chat Session History
Clear Chat History
|  |  | ML Chatbot Model | Receive Content-Aware Responses (Tailored to user's track data/profile)
Receive NCD-Specific Guidance
Display Safety Warnings / Rejections (If query is medically unsafe or out of scope)
|  |  | Personalized Assistance | Receive Motivational Responses
Group Fitness Challenge
|  |  | Friend System | Search for Users
CRUD Friend Requests (Send, Accept, Reject, Cancel)
View Friend List
View Friend Profile (Achievements, Avatar, Basic Stats)
|  |  | Team Challenges | View Available / Ongoing Group Challenges
Create Join / Leave Group Challenge
View Team Progress (Collective Steps, Distance, etc.)
View Challenge Rules and Duration
| Objective 3: Integrate social elements like Community Rankings to increase user engagement and retention through interactive and supportive in-app community. | Implementation of Group Fitness Challenge |  | See Current Group Fitness Challenge on Dashboard
|  |  | Community Rankings | View Community Leaderboard
Filter Leaderboard Views (Group Fitness Challenge Only)
|  |  | Performance Comparison | Stat Comparison with other Group
View Personal Rank in Group Leaderboard
Rewards and Leaderboard
|  |  | Leaderboard System | View Friend Leaderboard Through Dashboard (Allow Several Categories
View Leaderboard in Group Fitness Challenge

## For Checking
User Customization Phase 1: The Onboarding
Sub-Category / Module | Specific Features / Tasks | Notes / Remarks
Account Management (Settings) | Signup (Email, Password) | Prioritize SignUp over Login Missing "Already Have an Account"
| Personal Information |  | Move "The Basics, Weight Goals..." to First-time Login
Personal Fitness Information | First-Time Setup (The Basics, Weight Goals, Step Goals, Availability Schedule) | Change "The Basics to Personal Information", Move Current weight to Personal Information
CRUD Health Metrics (Age, Height, Current Weight)
CRUD Fitness Goals (Target Weight, Desired Activity Level, Schedule)
| Login |  | Notes / Remarks
CRUD Account Information (Username, Email, Password)
Manage Notification Settings (Workout Reminders, Inactivity Alerts)
Manage Privacy Settings (Profile Visibility)
Logout / Deactivate Account
Avatar Customization | Select / Update User Avatar
View Current Avatar in Profile
See Avatar in Dashboard
Dashboard Phase 2: The Landing
Sub-Category / Module | Specific Features / Tasks | Notes / Remarks
Fitness Data Management | Display Current / Next Activity Progress in Dashboard
Display Daily AI Generated Tips
See Fitness Goal Progress Bar in Dashboard
View Calculated BMI Status (Auto-updated based on weight inputs)
Quick Access & Snapshots | Display Leaderboard in Dashboard
Display Top Exercises in Dashboard
See Current Group Fitness Challenge on Dashboard
Show Achievements in Dashboard (Recently Unlocked / Close to Unlocking)
Fitness Buddy Chatbot Phase 3: The Core Value
Sub-Category / Module | Specific Features / Tasks | Notes / Remarks
Chat Interface | Open / Close AI Chat Window
Input Text Queries (Natural Language Questions)
View Chat Session History
Clear Chat History
AI Responses & Safety | Display AI Generated Responses
Receive Content-Aware Responses (Tailored to user's track data/profile)
Receive NCD-Specific Guidance
Display Safety Warnings / Rejections (If query is medically unsafe/out of scope)
Receive Motivational Responses
Training Program Phase 4: The Action
Sub-Category / Module | Specific Features / Tasks | Notes / Remarks
Exercise Library | See Exercise Library Through Training Program
See Selection of Exercises
Filter Exercise Selection
Search Through Exercise Selection
Show Exercise Details (Description, Video, Calories, Time, Difficulty)
Workout Calendar | See Calendar in Training Program
CRUD Workout Calendar
See Different Workouts For Each Selected Date
See Finished Exercise in Calendar
Workout Execution (Timer) | Start Exercise
Timer (Start, Pause, Finish)
Show Details in Timer (Steps, Distance, Pace, etc)
Exercise Progress (GPS, Machine Input, Duration, Timer Reps, Volume Distance)
Finish Exercise (Summary, Add Description, Images)
AI Adaptation | Ask AI For Updated Workout Calendar
Generate Adaptive Workout
Display Recommendations After Workout
Progress Tracking Phase 5: The Results
Sub-Category / Module | Specific Features / Tasks | Notes / Remarks
Activity History | See Activity History From Progress Report
Show Completed Activities in Activity History
Show Details of Completed Activities
Reports & Visualizations | Progress Report (Daily, Weekly, Monthly)
Track Fitness Goal (Step Count, Exercise Time, etc)
Show Graphs and Charts for Progress Reports
Show Graphs and Charts for Individual Activities / Challenges
Share Progress Report to Feed or Outside Apps
Rewards and Leaderboard Phase 6: The Motivation
Sub-Category / Module | Specific Features / Tasks | Notes / Remarks
Achievements | Achievement Unlocked Notification
View Achievements (All, Locked, Unlocked)
View Achievement Details (Locked, Unlocked)
Show Unlocked Achievement in Social Feed
Show Achievements in User Profile (Own Profile, Friends Profile)
CRUD Achievements Displayed
Show Achievement That Can be Unlocked From Particular Activity / Challenge
Community & Friends | Search for Users
CRUD Friend Requests (Send, Accept, Reject, Cancel)
View Friend List
View Friend Profile (Achievements, Avatar, Basic Stats)
Leaderboards | View Community Leaderboard
View Friend Leaderboard Through Dashboard
View Leaderboard in Group Fitness Challenge
Filter Leaderboard Views (Group Fitness Challenge Only)
Stat Comparison with other Group
View Personal Rank in Group Leaderboard
Group Fitness Challenge
View Available / Ongoing Group Challenges
Create / Join / Leave Group Challenge
View Team Progress (Collective Steps, Distance, etc.)
View Challenge Rules and Duration

## Test2
Problem Statement | Objectives | Scopes | Features | Remarks
How can a mobile health application be designed to provide a platform for Filipino non-gym-goers to overcome the specific motivational barriers, such as lack of time, guidance, and training plan, that prevent them from adhering to a consistent cardiovascular exercise routine? | Main Objective: Design and develop an adaptive, AI-driven mobile platform for Filipino non-gym-goers to overcome motivational barriers and deliver personalized cardio training. | Implementation of Personalized Goal-Setting Structure for planning and monitoring fitness routines aligned with WHO guidelines. | DASHBOARD (MODULE)
- Performance Overview
- Dynamic Visualizations (charts, progress indicators)
- Health "Bits and Tips" Section.
REWARDS & LEADERBOARD (MODULE)
- Achievement Badges
- Points/Ranking System
- Leaderboard Display.
| Objective 1: Implement personalized goal-setting and progress visualization through an interactive dashboard. | Implementation of Progress Tracking Analyzing user metrics (like BMI) to generate impactful, accurate progress visualizations. | PROGRESS TRACKING (MODULE)
- Daily, Weekly, Monthly Trend Charts
- Statistical Summaries (Calories, Active Time)
- Goal Attainment Monitor.
| Objective 2: Provide an Adaptive Training System to generate personalized workout activities tailored to real-time schedules. | Deployment of Machine Learning Algorithm A fully adaptive plan that adjusts intensity and duration based on fatigue and performance history. | TRAINING PROGRAM (MODULE)
- AI-Generated Adaptive Plans
- Exercise Library (Multimedia)
- Workout Timer & Session Tracker
| Objective 3: Provide real-time, context-based hints and guidance via an AI companion. | Implementation of AI-Enabled Companion Powered by a curated knowledge base to deliver instant feedback and training advice. | FITNESS AI CHATBOT (MODULE)
- Intelligent Conversational Assistant
- AI Recommendation Engine
- Adaptive Reminders.
| Objective 4: Integrate social elements to increase engagement and retention through a supportive community. | Implementation of Social Ecosystem Recreating gym dynamics via localized peer connections and collaborative challenges. | GROUP FITNESS (MODULE)
- Friend System & Performance Comparison
- Community Rankings
- Team Challenges.

## Try (to Edit)
| Objectives | Scopes | Features | Features | Remarks
How can a mobile health application be designed to provide a platform for Filipino non-gym-goers to overcome the specific motivational barriers, such as lack of time, guidance, and training plan, that prevent them from adhering to a consistent cardiovascular exercise routine? | Main Objective: The primary objective of this study is to design and develop an adaptive, AI-driven mobile platform for Filipino non-gym-goers, which leverages gamified engagement to overcome specific motivational barriers (lack of time, guidance, and planning) and deliver personalized cardiovascular training to promote consistent adherence and mitigate NCD risks. | Implementation of Dashboard Implementation of Rewards and Leaderboard Implementation of User Customization | User Customization
|  |  | Account Management (Settings) | Signup (Email, Password, The Basics, Weight Goals, Step Goals, Availability Schedule, Final Review) | Get Started
|  |  |  | Login | Signup
|  |  |  | Personal Information | Login
|  |  |  | Tutorial | CRUD Information
|  |  |  | CRUD Account Information (Username, Email, Password) | Customize Avatar
|  |  |  | Manage Notification Settings (Workout Reminders, Inactivity Alerts) | Home/Dashboard
|  |  |  | Manage Privacy Settings (Profile Visibility) | Training
|  |  |  | Logout / Deactivate Account | Calendar
|  |  | Personal Fitness Information | CRUD Health Metrics (Age, Height, Current Weight) | Generate AI Plan | --
|  |  |  | CRUD Fitnness Goals (Target Weight, Descired Activity Level) | Exercise | Instructions (Video)
|  |  | Avatar Customization | View Current Avatar in Profile | Finish Exercise | Specify
Progress Tracking
Home/Dashboard
Current Exercise
|  |  |  | See Avatar in Dashboard | Chart
|  |  |  | Select / Update User Avatar | Metrics
|  |  | Training Program |  | Chatbot
|  |  | Exercise Library (Instructional Videos) | See Exercise Library Through Training Program
|  |  |  | See Selection of Exercises | Home/Dashboard | Friends Leaderboard
|  |  |  | Filter Exercise Selection | Bits n Tips | Achievements
|  |  |  | Search Through Exercise Selection | Profile
Show Exercise Details (Description, Video, Calories, Time, Difficulty)
|  |  | Workout Calendar Scheduler | See Calendar in Training Program | Edit Profile
|  |  |  | See Different Workouts For Each Selected Date | Social
|  |  |  | CRUD Workout Calendar | Group Challenge
Ask AI For Updated Workout Calendar
|  |  | Workout Tracker and Timer | See in Exercises
Timer (Start, Pause, Finish)
| Objective 1: Implement personalized goal-setting and progress visualization through an interactive cardio activity dashboard to enhance user motivation and engagement. | Implementation of Progress Tracking Implementation of User Customization |  | Show Details in Timer (Steps, Distance, Pace, etc)
|  |  | AI-Generated Adaptive Workout Plan and Recommendations | Generate Adaptive Workout
Display Recommendations After Workout
Progress Tracking
|  |  | Workout Logs / Activity Reports(Daily, weekly, monthly progress report) | Progress Report Daily, Weekly, Monthly)
Track Fitness Goal (Step Count, Exercise Time, etc)
View Calculated BMI Status (Auto-updated based on weight inputs)
See Fitness Goal Progress Bar in Dashboard
See Activity History From Progress Report
Show Completed Activities in Activity History
Show Details of Completed Activities
|  |  | Export and Share Feature | Share Progress Report to Feed or Outside Apps
|  |  | Data Visualization for Performance Trends | Show Graphs and Charts for Progress Reports
Show Graphs and Charts for Individual Activities / Challenges
Rewards and Leaderboard
|  |  | Achievement Badge System | Achievement Unlocked
View Achievements (All, Locked, Unlocked)
View Achievement Details (Locked, Unlocked)
Show Achievements in Dashboard (Recently Unlocked / Close to Unlocking)
Show Unlocked Achievement in Social Feed
Show Achievements in User Profile (Own Profile, Friends Profile)
CRUD Achievements Displayed
| Objective 2: Provide an Adaptive Training System to generate personalized workout activities and user support, tailored to the user's real-time schedule and activity goal. | Implementation of Training Program Implementation of AI Chatbot |  | Show Achievement That Can be Unlocked From Particular Activity / Challenge
Dashboard
|  |  | Fitness Data Management (BMI, calories burned, steps taken, active minutes) | Display Current / Next Activity Progress in Dashboard
Display Daily AI Generated Tips
|  |  | Leaderboard Data Management (Current placement, challenges won) | Display Leaderboard in Dashboard
|  |  | Workout Data Management (Top exercises) | Display Top Exercises in Dashboard
AI Chatbot
|  |  | Chat Interface | Open / Close AI Chat Window
Input Text Queries (Natural Language Questions)
Display AI Generated Responses
View Chat Session History
Clear Chat History
|  |  | ML Chatbot Model | Receive Content-Aware Responses (Tailored to user's track data/profile)
Receive NCD-Specific Guidance
Display Safety Warnings / Rejections (If query is medically unsafe or out of scope)
|  |  | Personalized Assistance | Receive Motivational Responses
Group Fitness Challenge
|  |  | Friend System | Search for Users
CRUD Friend Requests (Send, Accept, Reject, Cancel)
View Friend List
View Friend Profile (Achievements, Avatar, Basic Stats)
|  |  | Team Challenges | View Available / Ongoing Group Challenges
Create Join / Leave Group Challenge
View Team Progress (Collective Steps, Distance, etc.)
View Challenge Rules and Duration
| Objective 3: Integrate social elements like Community Rankings to increase user engagement and retention through interactive and supportive in-app community. | Implementation of Group Fitness Challenge |  | See Current Group Fitness Challenge on Dashboard
|  |  | Community Rankings | View Community Leaderboard
Filter Leaderboard Views (Group Fitness Challenge Only)
|  |  | Performance Comparison | Stat Comparison with other Group
View Personal Rank in Group Leaderboard
Rewards and Leaderboard
|  |  | Leaderboard System | View Friend Leaderboard Through Dashboard (Allow Several Categories
View Leaderboard in Group Fitness Challenge

## Try
Problem Statement | Objectives | Scopes | Features | Features | Remarks
How can a mobile health application be designed to provide a platform for Filipino non-gym-goers to overcome the specific motivational barriers, such as lack of time, guidance, and training plan, that prevent them from adhering to a consistent cardiovascular exercise routine? | Main Objective: The primary objective of this study is to design and develop an adaptive, AI-driven mobile platform for Filipino non-gym-goers, which leverages gamified engagement to overcome specific motivational barriers (lack of time, guidance, and planning) and deliver personalized cardiovascular training to promote consistent adherence and mitigate NCD risks. | Implementation of Dashboard Implementation of Rewards and Leaderboard Implementation of User Customization | User Customization
|  |  | Account Management (Settings) | Signup (Email, Password, The Basics, Weight Goals, Step Goals, Availability Schedule, Final Review) | Move The Basics, Weight Goals, Step Goals, Availability Schedule, Final Review to First time Login
Login
Personal Information
|  |  |  | Tutorial | User Customization
|  |  |  | CRUD Account Information (Username, Email, Password) | - Account Management
|  |  |  | Manage Notification Settings (Workout Reminders, Inactivity Alerts) | -- Signup
|  |  |  | Manage Privacy Settings (Profile Visibility) | -- Login
|  |  |  | Logout / Deactivate Account | -- Personal Information
|  |  | Personal Fitness Information | CRUD Health Metrics (Age, Height, Current Weight) | -- Tutorial
|  |  |  | CRUD Fitnness Goals (Target Weight, Descired Activity Level) | -- CRUD Acct Info
|  |  | Avatar Customization | View Current Avatar in Profile | - Personal Fitness Infor
|  |  |  | See Avatar in Dashboard | -- Health Metrics
|  |  |  | Select / Update User Avatar | -- Fitness Goals
Training Program
|  |  | Exercise Library (Instructional Videos) | See Exercise Library Through Training Program
See Selection of Exercises
Filter Exercise Selection
Search Through Exercise Selection
Show Exercise Details (Description, Video, Calories, Time, Difficulty)
|  |  | Workout Calendar Scheduler | See Calendar in Training Program
See Different Workouts For Each Selected Date
CRUD Workout Calendar
Ask AI For Updated Workout Calendar
|  |  | Workout Tracker and Timer | See in Exercises
Timer (Start, Pause, Finish)
| Objective 1: Implement personalized goal-setting and progress visualization through an interactive cardio activity dashboard to enhance user motivation and engagement. | Implementation of Progress Tracking Implementation of User Customization |  | Show Details in Timer (Steps, Distance, Pace, etc)
|  |  | AI-Generated Adaptive Workout Plan and Recommendations | Generate Adaptive Workout
Display Recommendations After Workout
Progress Tracking
|  |  | Workout Logs / Activity Reports(Daily, weekly, monthly progress report) | Progress Report Daily, Weekly, Monthly)
Track Fitness Goal (Step Count, Exercise Time, etc)
View Calculated BMI Status (Auto-updated based on weight inputs)
See Fitness Goal Progress Bar in Dashboard
See Activity History From Progress Report
Show Completed Activities in Activity History
Show Details of Completed Activities
|  |  | Export and Share Feature | Share Progress Report to Feed or Outside Apps
|  |  | Data Visualization for Performance Trends | Show Graphs and Charts for Progress Reports
Show Graphs and Charts for Individual Activities / Challenges
Rewards and Leaderboard
|  |  | Achievement Badge System | Achievement Unlocked
View Achievements (All, Locked, Unlocked)
View Achievement Details (Locked, Unlocked)
Show Achievements in Dashboard (Recently Unlocked / Close to Unlocking)
Show Unlocked Achievement in Social Feed
Show Achievements in User Profile (Own Profile, Friends Profile)
CRUD Achievements Displayed
| Objective 2: Provide an Adaptive Training System to generate personalized workout activities and user support, tailored to the user's real-time schedule and activity goal. | Implementation of Training Program Implementation of AI Chatbot |  | Show Achievement That Can be Unlocked From Particular Activity / Challenge
Dashboard
|  |  | Fitness Data Management (BMI, calories burned, steps taken, active minutes) | Display Current / Next Activity Progress in Dashboard
Display Daily AI Generated Tips
|  |  | Leaderboard Data Management (Current placement, challenges won) | Display Leaderboard in Dashboard
|  |  | Workout Data Management (Top exercises) | Display Top Exercises in Dashboard
AI Chatbot
|  |  | Chat Interface | Open / Close AI Chat Window
Input Text Queries (Natural Language Questions)
Display AI Generated Responses
View Chat Session History
Clear Chat History
|  |  | ML Chatbot Model | Receive Content-Aware Responses (Tailored to user's track data/profile)
Receive NCD-Specific Guidance
Display Safety Warnings / Rejections (If query is medically unsafe or out of scope)
|  |  | Personalized Assistance | Receive Motivational Responses
Group Fitness Challenge
|  |  | Friend System | Search for Users
CRUD Friend Requests (Send, Accept, Reject, Cancel)
View Friend List
View Friend Profile (Achievements, Avatar, Basic Stats)
|  |  | Team Challenges | View Available / Ongoing Group Challenges
Create Join / Leave Group Challenge
View Team Progress (Collective Steps, Distance, etc.)
View Challenge Rules and Duration
| Objective 3: Integrate social elements like Community Rankings to increase user engagement and retention through interactive and supportive in-app community. | Implementation of Group Fitness Challenge |  | See Current Group Fitness Challenge on Dashboard
|  |  | Community Rankings | View Community Leaderboard
Filter Leaderboard Views (Group Fitness Challenge Only)
|  |  | Performance Comparison | Stat Comparison with other Group
View Personal Rank in Group Leaderboard
Rewards and Leaderboard
|  |  | Leaderboard System | View Friend Leaderboard Through Dashboard (Allow Several Categories
View Leaderboard in Group Fitness Challenge

## Sheet2
Problem Statement | Objectives | Scopes | Features | Remarks
How to utilize a digital game-based learning framework in providing supplemental learning tools for reading comprehension that are adaptive and engaging for Filipino learners?” | Main Objective: Support the improvement of students reading comprehension skills and overall literacy through developing an innovative and accessible tool that combines educational content with game-based mechanics and storytelling presented in a visual novel-style format. | Implementation of Web Dashboard - Learner Overview - Grade-Level Analytics - Viewable Graphs and Tables - Downloadable Reports Implementation of Story Mode - Unlockable Badges Implementation of Challenge Mode - Performance Summary - Instant Feedback System Implementation of Tutorial Mode - Interactive Application Walkthrough | Dashboard (MODULE)
- Story Progress of Class and Individual
- Summary of Challenge Attempts (Scoring)
Admin Reports (MODULE)
- Downloadable Report of Dashbaord (PDF)
GAME TUTORIAL (MODULE)
Game Instruction
- Demonstrate How-to-Play (Text Extract)
- Demonstrate How-to-Play (Two Truths)
- Demonstrate How-to-Play (Statement Scrutinize)
ACHIEVEMENTS AND LEADERBOARD (MODULE)
Display Leaderboard
- Top 10 Scores for each game modes
Display Achievement in Profile Page
- Display Achievement Title
- Display Achievement Details
- Display Date of Acquisition
Displaying of Badges in Profile Page
- Display Badge Image & Details
| Objective 1: Integrates narrative-driven storytelling with interactive reading comprehension activities for Filipino students through a visual novel-style format.​ | Implementation of a Story-Mode - Story-Based Reading Gameplay - Multiple Story Levels - Embedded Gameplay Loop | STORYBOARD (MODULE)
Selection of Story Gamemode
Selection of Worlds (Story)
Selection of Levels
Narration (Text-To-Speech, Navigation of Dialogue)
--
Player Choices & Branching Logic
Proceed to Activity
Proceed to Story Level (Lock)
| Objective 2: Implement interactive comprehension tasks where learners engage through various literary passages and excerpts such as poems, novels, and inspirational quotes to foster active reading and deeper understanding. | Implementation of Challenge Mode - Multiple Gamemodes (Text Extraction, Two Truths and a Lie, Statement Scrutinize) | CHALLENGE MODE (MODULE)
Selection of Challenge Gamemode
Selection of Activity Type (Text Extraction, Two Truths and a Lie, Statement Scrutinize)
Selection of Theme
Text Extraction
- 5 Questions
- Drag and Drop
- Pop Up Feedback After Every Question
- AI Assistant (User Message, Chatbot Response)
- Real Time Score Display
Two Truths and a Lie
- 5 Questions
- 3 Choices, 2 are incorrect, 1 is correct
- Clickable Buttons to select the incorrect statement (correct answer)
- Pop Up Feedback After Every Question
- AI Assistant (User Message, Chatbot Response)
- Real Time Score Display
Statement Scrutinize
- 5 Questions
- Dynamic Statement Choice
- Multi-select of words after Doubting Statement
- Dynamic changing of sprites per statement traversal
- Pop Up Feedback After Every Question
- AI Assistant (User Message, Chatbot Response)
- Real Time Score Display
| Objective 3: Provide practice sets by utilizing an AI system to automatically generate reading prompts with relevant reading comprehension questions. | Implementation of Challenge Mode - LLM-Generated Reading Tasks | AI ASSISTANT (MODULE)
Generation of Reading Comprehension Task
- Filter of Correct Format
--- Text Extract: text_passage;question;answer
--- Two Truths: text_passage;statement1¦statement2¦statement3;num_answer
--- Statement Scrutinize: text_passage;statement1¦statement2¦statement3;num_answer¦evidence
| Objective 4: Provide real-time, context-based hints and guidance to support learners in answering comprehension questions effectively by developing an AI companion. | Implementation of Challenge Mode - AI-Enabled Companion | AI ASSISTANT (MODULE)
User Messaging Function
Chatbot Response Function

## NULL
One pressing challenge is the limited opportunity for Filipino students to engage in reading comprehension practice beyond the classroom. As noted by Idulog (2023), Without accessible and engaging platforms to reinforce reading habits at home or in informal environments, students are unable to develop consistent reading routines or deepen their understanding through independent learning. This disconnect between in-school instruction and at-home reinforcement hinders the development of strong reading habits and foundational skills.
Integrates narrative-driven storytelling with interactive reading comprehension activities for Filipino students through a visual novel-style format.​
The application will focus on enhancing English reading comprehension through interactive, story-based gameplay. By embedding reading tasks into a visual novel and game format, the system will simulate immersive, real-life reading experiences in English that promote vocabulary acquisition, context interpretation, and inferencing. Additionally, these narratives drawing from English-translated Filipino storybooks, folktales, and familiar community settings, will naturally encourage cultural relevance and connection. This will enable learners to connect new English concepts to their existing cultural schema. This platform is intended to support second-language acquisition by increasing student motivation and engagement by combining entertainment with literacy learning that feel meaningful and relatable to Filipino students.
STORYBOARD (MODULE)
Moreover, traditional classroom materials, such as textbooks and worksheets, are often static, lacking the interactivity needed to encourage active reading. (DepEd, 2023; Dludla et al., 2024). This approach reduces students’ ability to engage critically with texts, especially when it comes to poetry and literature that require interpretation and deeper comprehension. The absence of multimedia tools, gamified learning elements, and scaffolded reading environments contributes to a passive reading culture, making it difficult for students to relate to or internalize complex texts. (Dludla, T., et al., 2024)
Implement interactive comprehension tasks where learners engage through various literary passages and excerpts such as poems, novels, and inspirational quotes to foster active reading and deeper understanding.
The application will incorporate a wide range of English-language texts, including literary excerpts, short poems, and thought-provoking quotations, tailored to the comprehension levels and grade levels of Philippine students. Additionally, these reading passages will be followed by structured tasks via drag and drop reading comprehension questions designed to assess literal, inferential, and critical understanding. This allows support of development in the core English reading skills such as skimming, scanning, context clue analysis, and text interpretation.
PRACTICE MODE (MODULE)
Furthermore, students often run out of meaningful practice materials, especially outside school hours, as current educational apps and modules usually offer a fixed set of questions, limiting continuous improvement. This limitation in available content leads to repetitive learning experiences, diminishing motivation and failing to address diverse learner needs across reading levels and interests. (PIDS, 2023)
Provide practice sets by utilizing an AI system to automatically generate reading prompts with relevant reading comprehension questions.
This mode offers continuous practice in English reading through AI-generated texts and comprehension questions. The AI-enabled system will curate reading materials across various genres and pre-set difficulty levels, ensuring learners have access to personalized, level-appropriate English content. By supplying limitless practice opportunities, this supports mastery through repetition, encourages independent learning, and helps address the scarcity of reading materials in traditional classrooms.
AI ASSISTANT (MODULE)
Generation of Reading Comprehension Task
In addition, as students encounter difficulties in understanding complex prompts on their own, they do not have immediate access to a teacher or tutor outside of class to ask for assistance or get feedback on their work. As a result, students become discouraged when they cannot clarify confusing instructions or verify their answers, which ultimately slows down learning progress and affects confidence in comprehension tasks (Fitria, T.N., 2021).
Provide real-time, context-based hints and guidance to support learners in answering comprehension questions effectively by developing an AI companion.
The AI-enabled companion will act as a reinforcement for an intelligent support system that offers hints, definitions, and guidance in English to support learners as users answer comprehension questions. By providing timely, contextual feedback in English, the AI-enabled companion will help students better understand text structure, unfamiliar vocabulary, and nuanced meanings. The AI-enabled companion guidance is aimed at developing learner confidence, improving accuracy, and building independent reading strategies in English.
AI ASSISTANT (MODULE)